GET

THAT

GRANT!

#### A Guide to Writing

#### Standard Grant Proposals For

#### The Maryland State

Department of Education

Copyright © 2000

by

Maryland State Department of Education

Prepared by the Office of Grant Management & Resource Development

CONTENTS

INTRODUCTION..............................	1

THE REVIEW PROCESS........................	2

BEFORE YOU BEGIN WRITING..................	3

THE BIG PICTURE...........................	5

DISSECTING THE PROPOSAL ..................	8

The Cover Sheet.......................	8

The Abstract  ........................	9

The Table of Contents ................	10

The Needs Assessment  ................	11

Project Outcomes .....................	12

Implementation Plan ..................	15

Evaluation Plan.......................	17

Management Plan ......................	20

Integration With Educational Reform ..	23

Future Plans .........................	24

Budget ...............................	25

Appendices ...........................	29

WHY ALL THE FUSS..........................	31

## INTRODUCTION

As funds for special projects shrink, it becomes increasingly important to award grants to projects that demonstrate the greatest potential for success.  This handbook is intended to offer insight into how to write the best possible proposal.

The best projects begin before a competition is announced.  A prepared applicant will research a problem, set goals, gather partners and determine a course of action long before a funder is identified.   Conducting proper needs assessments and constructing effective implementation plans often take more time than is allowed by the submission deadline.

Here are the major steps in the grant writing process:

- Identify a problem affecting a particular target group.

- Conduct a needs assessment.  How serious is the problem?  Document it.

- Establish outcomes you wish to achieve.

- Conduct research to identify the strategies and activities that would be most

effective in solving your problem.

- Write a concept paper outlining your need, outcomes, strategies and activities.

- Identify the partners you need and the roles they should play in solving the

problem.

- Use your concept paper to get approval of your ideas within your organization.

- Use your concept paper to get your partners to sign on to your project.

- Identify possible funding sources. (MSDE?)

- Upon getting the Request for Proposal (RFP), read it all the way through the

first time.

- Tailor your project to match the priorities identified in the RFP.  What is the

potential funder looking for?

- Attend the technical meeting!  Ask questions!

- Write the proposal, following the directions precisely.

- Get letters of commitment from project partners.

- Have a disinterested party read and critique your proposal, and make revisions.

- Get final approval from your organization to submit the proposal.

- Submit your proposal by the deadline and in the format required.

.

## THE REVIEW PROCESS

- The Receipt: You receive a receipt upon delivering your submission package to the friendly person at MSDE.  The receipt indicates that you have submitted your proposal and will be signed with the date and time.

- The Prescreen: Immediately after the submission deadline, proposals are checked to ensure that they meet the submission requirements.  Words are counted, margins measured, font sizes assessed, and sections checked.  Proposals not meeting the prescreen requirements are disqualified at once!

- The Review: Reviewers are trained and assigned proposals.  They read, score and comment upon your proposal.

- Oral Presentations: Because panel members may have questions about your proposal, they may require you to make an oral presentation on it.  Be prepared!

- Panel Recommendations: The panel makes recommendations based on the results of the reviewers’ scores and comments as well as the feedback from the oral presentations.   While the reviewers score projects based solely on the merits of their proposals, the review panel and/or the superintendent may consider other criteria such as geographic distribution or previous awards.

- Board Approval: On many grants, the State Board of Education makes the final decision on who gets the money.

- Award Notification: After the final decisions regarding the awards have been made, winners are notified of their awards.  Now comes the hard part if you’re a winner. Implementing successfully the plan you’ve submitted.

Before You Begin Writing

What you do before you write your proposal dramatically affects the quality of the project. There is often very little  “turn-around” time between the RFP’s release date and its submission deadline.  Therefore, it’s important to begin planning your project before funds are identified.  You will probably experience major time crunches if you have to forge partnerships and create a project after the RFP is released.  This section discusses processes that can be done before you start writing the proposal.

# 1) IDENTIFY A PROBLEM

Good projects start with a problem, not a funding source.  Ask teachers, administrators, parents, and even students what they think the big problems are.  Don’t look for solutions at this point.  That comes later.  Categorize the problems according to severity.

2) CONDUCT A NEEDS ASSESSMENT

This doesn’t have to include extensive research or cost a lot of money.  Select the biggest problem, and identify the factors that contribute to the problem.  Ask people why they think the problem is occurring.  Read studies that provide support for your problem as a real problem.

3) WRITE A CONCEPT PAPER

A concept paper is a brief description of the intended proposal.  It describes why the project is needed, what your project will accomplish, and the roles of the project partners.  Concept papers are not intended to be shared with potential funders, but rather, with essential personnel within your organization and your project's potential partners.  Concept papers generally are no more than a few pages in length.

WHY WRITE A CONCEPT PAPER?

It may seem counterproductive to add unnecessary steps to the proposal writing process.  Nonetheless, a concept paper will save you time, effort, and frustration.

The concept paper's primary purpose is to assist you in receiving approval from your organization before spending large amounts of time researching and writing a proposal.  Getting approval for your idea before you write a proposal will save you from making major last-minute overhauls.  Your idea of the project may be different from your superiors' ideas.  A concept paper will keep everyone singing from the same sheet of music.

The other major reason to write a concept paper is that it significantly reduces the amount of time needed to negotiate partnerships.   It's much easier to get partners to sign on to an idea than a funding source.  Approaching partners with only an RFP or a funding-lead often leads to the "pigs at a trough" syndrome.  It's easy to get partners to agree to split the money, but it usually turns into a contest as to who can get the biggest piece of pie.  Projects that get started this way often lack coherence and direction.  Reviewers can spot this.  Having a concept paper up front enables potential partners to say quickly whether they can or can't provide the services you need.  This makes shopping for partners an efficient and less contentious task.

WHAT'S IN A CONCEPT PAPER?

- Start with a brief problem statement.  State why this project is necessary.  Don't suggest solutions in the problem statement; they come later.

Examples:

- "Students at XYZ elementary score far below the state average on the standardized math test."

- "Drug-related crimes in South Acmeville have risen 20% in the past five years."

- The next paragraph should paraphrase the objectives you will accomplish by the end of the project.

Examples:

- "Fifth grade standardized math scores will increase by 20%."

- "By the end of this project, burglaries will decrease by 7%.”

- Follow your objectives with a description of the strategies you intend to employ to achieve them  List each strategy. Remember each strategy must address your objectives.

- List all the possible partners you will need and describe their roles, responsibilities and the contributions they should make to the project.  Spend some extra time here; your partners will thank you.  Don't forget to include people in your own organization.

- Finally, include any information that is relevant to the planning of the project. Questions you might want to answer are: "How does this project fit with our master plan?", "By whom and how will this project be managed?", "What are the benefits of this project?", "How will this project be evaluated?"

- If possible, include a rough budget.  Since much of the project is defined by money, if you can give all key players an idea of how much they will have to work with, it can save you a lot of headaches later.

SOME FINAL THOUGHTS ON CONCEPT PAPERS

Concept papers are not written in stone.  They are preludes to negotiating the details of the final proposal.  Don't be afraid to rewrite your paper as facts, partners, priorities and circumstances change.  Date your paper so partners know which is the latest version.   By writing and rewriting your concept paper, you are actually filling in the details of your proposal.

THE BIG PICTURE

A proposal contains many sections.  These sections are dependent upon and related to the previous sections.  The entire proposal should function as one coherent document with each section flowing logically from one to the next.

*	Standard proposals submitted to MSDE should contain the following sections, in the order of their appearance on this page:

|  |  | Cover Sheet |  | The first page of the proposal containing the title, the name of your organization and authorized signatures. |  |
| --- | --- | --- | --- | --- | --- |
|  |  | Abstract |  | A one-page overview of the entire proposal. |  |
|  |  | Table of Contents |  | A guide to the contents of the proposal. |  |
|  |  | Needs Assessment |  | A study demonstrating a need for the proposed project. |  |
| Project Narrative |  |  | Outcomes |  | A statement of what the project is intended to achieve. |
|  |  |  | Implementation Plan |  | A plan for achieving the stated outcomes. |
|  |  |  | Evaluation Plan |  | A plan for evaluating the success of the project. |
|  |  |  | Management Plan |  | A plan for coordinating and directing the efforts to support the implementation and evaluation plans. |
|  |  |  | Integration With Education Reform |  | A discussion of how the proposed project helps meet school, community, LEA, MSDE and national goals. |
|  |  | Future Plans |  | A discussion of how the project will continue past the funding period. |  |
|  |  | Budget |  | A detailed report of all requested and in-kind financial resources. |  |
|  |  | Appendices |  | Any relevant information not required in the project narrative, including resumes of key personnel and letters of commitment from project partners. |  |

This chart belows illustrates how all the major sections of the proposal are interrelated.

Establishes the problem and is the foundation upon which the rest of the proposal is built.

The project’s expected achievements.  They are based on the needs assessment and consist of goals, objectives and milestones.

The ultimate intended outcome.   Usually takes several years to accomplish.

Outcomes derived from the goal.  They state what the applicant will accomplish by the end of each year or designated phase.

Consists of the strategies and activities used to accomplish the stated outcomes.

Outcomes derived from objectives. They state what the applicant will accomplish by certain points during each phase or year.

Directs all actions necessary to support the implementation and evaluation of the project.

General approaches used to achieve the stated outcomes.

- The specific instances of direct service described by the strategies.

A study to assess how effectively the implementation plan attains the outcomes.

Describes the financial resources needed to fund the entire project.

| RED FLAG Proposals should speak with one voice. Sections that are written in multiple styles, or use various fonts often have several authors, who have very different ideas about the project. Make sure each section follows logically from the previous section. | STYLE For the most part, a proposal is scored according to the merits of each of its sections. Nonetheless, a proposal that does not follow basic rules of style can be difficult to read and critique. A well-written proposal will: - Avoid jargon. - Define all acronyms. - Not use the first person. - Eliminate run-on sentences. - Use concise language. - Be free of typos and grammatical errors. - Avoid metaphors or flowery language. - Not make emotional appeals. A good case is built on research and reason. - Use sections that logically follow from previous sections. - Support all facts, even the seemingly trivial ones. The reader should be able to answer the “How do you know?” question for any assertion made. |
| --- | --- |

DISSECTING THE PROPOSAL

THE COVER SHEET

The cover sheet is reviewed in the prescreen process and is generally not scored. The cover sheet makes the first impression the reader has of the project, however, and can indicate a great deal about the professionalism with which the project proposal was prepared.  A good cover sheet contains only the information requested by the RFP, and in the order specified.

St. Acme County Public Schools

Meeting the State Math Exam Standards

A Comprehensive Approach to

Improving 7th Grade Performance

Project Contact:

Dr. Jane Smith

St. Acme Middle School

300 Smart Street

Acme City, Maryland  21222

Telephone (410) 555-5555

Facsimile (410) 555-5554

Project Partners:

Acme City Chamber of Commerce

St. Acme General Hospital

St. Acme Community College

Amount Requested: $200,000

Dr. Joanna Eljefe                                                               Date

Superintendent, St. Acme County Public Schools

An effective title will:

- Be concise and explicit.

- Focus on the outcomes to be achieved, not the methods used.

- Often use a subtitle to clarify the main title or to indicate the nature of the project.

- Not be cute.

- Avoid acronyms.

Avoid jargon.

Joanna ElJefe      1/23/98

- Avoid words that add nothing to the reader’s understanding, such as “A Study on...” or “A Proposal for.…”

- Not list the project’s location.

Examples:

Poor Title:   	Students Making Inroads to Learning Excellence

Uses a ‘cute’ acronym (S.M.I.L.E.)

Poor Title: 	Funding Staff Development

Focuses on funding, not on outcomes

Poor Title:	Installing LAN Systems to Promote School Interconnectivity

Uses Jargon

Effective Title:   Raising SAT Scores For First Generation College Bound Students

| RED FLAG Abstracts have word limits and proposals have page limits. Conciseness is a virtue. Well developed proposals use every word and page to convey as much information about the project as possible. Failure to use all available space tells reviewers that the project’s details have not been planned thoroughly. | THE ABSTRACT The abstract is a brief overview of the entire project. It should summarize information from the needs assessment, outcomes, implementation plan, evaluation plan and management plan. If separated from the rest of the proposal, the abstract must stand on its own. There is usually a word limit of 250 to 300 words. A compelling abstract will present the following information: - The problem to be addressed. - The goals and objectives of the project. - The strategies and activities to be used. - Who will be served by the project. - Where the project will be conducted. - The project’s time frame. - The qualifications of the participating organizations and staff. - The benefits of the project. In addition, the abstract will: - Use concise language. - Present an overview of the entire project that closely matches the Proposal Narrative. - Not exceed the word limit. |
| --- | --- |
| RED FLAG A table of contents that does not match the page numbers in the proposal is often a sign of last-minute writing. Last- minute writing can result from a lack of scheduling, poor management skills, or contentious partnerships. Check to see that page numbers in your table of contents match those in your proposal. | THE TABLE OF CONTENTS The table of contents is intended to help the reader. While it is not scored, it gives the reviewer some insight on how carefully the project was constructed. Here are a few page numbering conventions: - The cover sheet is not numbered but is considered to be page “i” (lower case, Roman numeral one). - The abstract is number “ii” (lower case, Roman numeral two). - The table of contents is not listed in the table of contents. - Table of contents pages are numbered iii, iv, etc. - The needs assessment is the first page of the Project Narrative and is numbered “1". Subsequent pages of the Project Narrative are numbered consecutively. - If the budget is considered part of the Project Narrative, it will be numbered accordingly. Otherwise the budget will have specially designated page numbers such as “B-1, B-2, B-3 .…” - Appendices will be labeled “Appendix A, Appendix B, Appendix C .…” |
| RED FLAG Don’t try to “snow” reviewers with a blizzard of irrelevant statistics! A good needs assessment contains only data relevant to the problem. Teen pregnancy rates in a proposal trying to reduce drug use only confuses the issue and indicates a program without a clear direction. | THE NEEDS ASSESSMENT A compelling proposal will have a clearly-defined problem illustrated by a needs assessment. A needs assessment is a systematic review of information collected from a variety of sources, analyzed to determine strengths and weaknesses, and listed for action by order of priority. Relationships Don’t commit the crime of “backward engineering.” When some applicants receive the RFP, they often start dreaming about what they can buy with the money. After putting together a wish list, they work backwards, searching for a problem their solutions can fix. The best projects start with a needs assessment. The problem must be clearly identified before deciding which strategies to use, activities to conduct, or computers to buy. The needs assessment is the proposal’s foundation. If it isn’t constructed correctly, problems with the proposal grow exponentially through each section. An effective needs assessment will: - Clearly state the problem. - State what data were collected to confirm the existence of the problem, the sources of the data and the methods used to collect them. - Present easily measured quantitative data (e.g., test scores, absentee rates). - Present qualitative data in support of quantitative data (e.g., results from interviews, focus groups) - Use multiple methods to document the problem (e.g., surveys, analysis of school records, previous studies, focus groups). - Use multiple data sources (e.g., teachers, students, parents). - Use national or state data to establish the problem’s existence outside of the local area. - Use local data to document the problem in the local area. - State who is affected by the problem. - State when and where the problem exists. - Document the factors contributing to the problem. - Document current or past efforts to address the problem. - Show why those efforts failed or are inadequate to address the total need. - Discuss the organization’s history or expertise in dealing with the problem. - Discuss the consequences of not dealing with the problem. |

| Target Population Baseline Specific & quantitative level of success Long-Term Deadline Measurement Tool RED FLAG Outcomes must be achievable in the stated time frame. Any project that promises 100% success with all clients is setting itself up for failure. Goals must be ambitious, but they should never be unattainable. | PROJECT OUTCOMES It is critical that projects have measurable outcomes. All of the project’s outcomes must be stated in this section. Outcomes consist of goals, objectives and milestones. They state exactly what the project will accomplish. Relationships The best outcomes address problems established in the needs assessment. The presence of goals or objectives that are not rooted in the needs assessment indicates a project that suffers from backward engineering. Your reader should find easy answers to the question: “Why these outcomes?” The Goal A goal is a statement of the major desired measurable outcome, derived from the needs assessment. Goals state what the project team ultimately hopes to achieve. If the project is short-term, the goals may not be achieved by the end of the grant period. That’s acceptable. However, if the project covers multiple years, the goal should be achievable by the end of the grant period. It’s permissible to have more than one goal. However, the more goals a project has, the more unwieldy the project becomes. Therefore, it is preferable for a project to have just a few, focused goals. A well stated goal will: - Specify the problem to be addressed. - Specify the target population. - Be easily measured. A goal must demonstrate clear achievement. A strong goal statement will includes easily quantified indicators such as: test scores, absenteeism, grades, promotion rates, pre and post survey results, etc. While increasing children’s happiness may be laudable, “happiness” is difficult to measure and should not be the subject of a goal. - Refer to local data or standards. Goals should not be based on national statistics. - Be specific in its time frame, but long-term in its scope. - Have a realistic and achievable end. - Provide a baseline for comparison. By the year 2002, 70% of high school seniors, in the three participating high schools, who were reading below grade level in the ninth grade, will achieve a rating of satisfactory on the county high school reading examination, a 20% increase over current levels. |
| --- | --- |

| Target Population Baseline Specific & quantitative level of success Short Term Deadline Measurement Tool RED FLAG More isn’t better when it comes to outcomes. It’s acceptable to have more than one goal and more than a few objectives. However, the difficulty of implementing a project grows exponentially with the number of outcomes. | Objectives Objectives are statements of specific and measurable means to achieve the outcome(s) identified in the goal. If the project is long- term, objectives should be set for the end of each year or designated phase of the project. It is typical to have multiple objectives. Nonetheless, the fewer the objectives, the more directed the project. A good objective: - Is derived from a goal. - Is clearly stated. There should be no ambiguity as to what is to be accomplished. - Identifies the population(s) that are to be served and evaluated. - Is realistic. An objective must be attainable. It is unrealistic to expect that all students will achieve 4.0 grade point averages by the end of the grant. Unrealistic objectives invite failure. - Refers to state, local, or school-defined data-based areas and standards. - Is measurable. - Is short-term in its scope. Objective(s) should cover no more than one year. Considering the previously stated goal, a good objective might be: Considering the previously-stated goal, a good objective might be: By the end of the grant period, 15% of high school seniors, juniors, and freshmen in the three participating high schools who were reading below grade level in the ninth grade will achieve a rating of satisfactory on the county high school reading exam, a 10% increase over current levels. |
| --- | --- |

| RED FLAG Milestones are not items on a “To Do” list. Deadlines for management actions are not proper milestones. Having a computer lab installed by January, or conducting a workshop by the end of the year, does not demonstrate progress towards an objective. The purpose of milestones is to measure clients’ progress, not see how many things we can scratch off a list. | Milestones Evaluators, directors and steering committees will want to know what progress is being made periodically throughout the grant periods. If things aren’t going well, it’s important to know as soon as possible so that changes can be made. Because objectives cannot always be evaluated until the end of a funding cycle, each objective should have milestones associated with it. Milestones are the checkpoints that measure the periodic progress toward a stated objective. Typically, they are evaluated quarterly. However, the frequency with which they are evaluated is determined by the nature of the milestones and the data collected to evaluate them. A useful milestone: - Is clearly stated and avoids ambiguity. For example, stating that a condition will improve, without stating by how much, is considered ambiguous. - Is periodic. The quarterly evaluation of milestones is standard. The number of periods can differ depending on the nature of the milestone. - Is related to the objective. Milestones measure progress towards an objective by breaking the objective into steps, or by employing a good indicator of progress (e.g., quarterly grades as an indicator of MSPAP improvement). - Is measurable. As with objectives, milestones must be quantitatively demonstrable. - Takes into account the dynamics of the project. A project may take months before it can have an impact upon the clients, or the positive effects of a project may wane with time. Milestones should anticipate this and be gauged accordingly. Overly ambitious milestones can make a strong project look weak early on. If the objective is “There will be a 20% decrease in absenteeism over the 2000/01 school year, as measured by the end of the final marking period,” one set of corresponding milestones might be: - There will be a 2% decrease in absenteeism over the 2000/01 school year, as measured by the end of the first marking period. - There will be a 7% decrease in absenteeism over the 2000/01 school year, as measured by the end of the second marking period. - There will be a 13% decrease in absenteeism over the 2000/01 school year, as measured by the end of the third marking period. |
| --- | --- |

| RED FLAG “Why this strategy?” That’s the question you should answer. Did it work somewhere else? Has a similar strategy been shown to be effective? What experts recommend it? Solutions that are seemingly plucked from the air seldom have the desired results. | THE IMPLEMENTATION PLAN The implementation plan details how the project will accomplish its outcomes. This section consists of strategies and activities the project will employ. Relationships Strong outcomes are prerequisites for an effective implementation plan. The strategies and activities should be chosen on the basis of evidence that they will achieve the outcomes. Retrofitting problems and outcomes to match solutions often results in projects that have little positive impact on clients. Strategies The implementation plan begins with a discussion about the strategies used to accomplish the stated outcomes. Strategies are broad approaches (methods, procedures, techniques) employed to accomplish an objective. Strategies either address the problem detailed in the needs assessment or address factors that contribute to it. In this way, strategies are directly related to objectives. Every objective should have at least one strategy associated with it. Examples of strategies include professional development, after-school programs, mentoring, parent nights, etc. The introduction should cite studies, models, previous programs or some other evidence that the strategies and activities will result in the desired effects. Where else have these strategies been successfully employed? Which experts recommend them and why? Without this support, there is no evidence that the proposed strategies will work. All the strategies should work together as complementary parts of a whole. The implementation plan should look like one plan, not a hodgepodge of unrelated strategies. Make sure that the project’s clients have all or most of the services available to them. This section should answer the following questions: - What strategies are to be employed? - Why were these strategies chosen? How do they help achieve the stated outcomes? - What evidence is there to show that these strategies will be effective? - What other options were available, and why were they rejected? - How do the different strategies work together to achieve the outcomes? |
| --- | --- |

| RED FLAG Management actions should never be listed as activities. Projects that center their attention on hiring people and buying equipment lose sight of the fact that their main purpose is to make a difference for the client. | Activities Activities are things that happen “where the rubber meets the road.” They are the specific steps taken to accomplish the objectives. While strategies are general, activities are specific. Activities happen on specific dates and involve direct service to clients. If “mentoring” is a strategy, the mentoring session that happens on February 25th is an activity. Activities are grouped by strategy and, thus, are related to an objective. Actions that are not activities should be included in the management plan. While these actions are essential steps in conducting activities, they do not involve direct service themselves. Examples include purchasing equipment, hiring staff, developing curriculum, conducting evaluations and holding meetings. These actions should be addressed in the management plan but are not regarded as activities. Each activity should be listed (usually in a chart) and include the following information: - The objective the activity is expected to help achieve. - The strategy of which the activity is a part. - The date(s) the activity will occur. - A brief description of the activity. - The target audience. (Who will directly and indirectly benefit from this activity? Parents? Students? Teachers? Community Members? Administrators?) - The name and position of person(s) conducting the activity. Depending on the RFP, additional information may be required about each activity. This may include: - Number of people to be directly and indirectly served by the activity? - The evaluation procedures used to determine the activity’s success. The number of activities listed depends entirely upon the project. Large development projects may spend most of their money and effort in the management plan. A project can have only a few activities and still be effective. |
| --- | --- |

| RED FLAG An independent evaluator is not a substitute for an evaluation plan. You must provide a thorough discussion of evaluation methods, data collection, and data analysis. | THE EVALUATION PLAN If you win the grant, you will be required to demonstrate your project’s effectiveness. This requires an evaluation plan. Your plan must include details for conducting both ongoing evaluations and a final evaluation. Annual evaluations are necessary for projects that span multiple years. The evaluation plan will: - Pose questions the evaluation will answer. - Describe the process for data collection. - Identify who will conduct the evaluation. - Include staffing and budgetary resources that have been allocated for evaluation. - Present a clear plan to disseminate evaluation results. Relationships The evaluation plan depends on measurable outcomes and a focused implementation plan. If the outcomes are not properly stated, it’s impossible to know what success is. Without a definition of “success,” evaluation becomes impossible. Because the evaluation plan depends on previous sections, problems in preceding sections will be magnified here. If the evaluation plan is weak, chances are the problem starts in the earlier sections. Ongoing, Final & Annual Evaluations A strong project will have ongoing and final evaluations and an annual evaluation if the project spans multiple years. The ongoing evaluation measures the project’s success in achieving the milestones. The final evaluation happens at the end of the project, assesses the entire project, and measures the project’s success in achieving the goal(s). If the project spans multiple years, annual evaluations assess each year or funding cycle and measures the project’s success in achieving the objectives. Ongoing, final and annual evaluations should: - Use quantitative data such as test scores or attendance rates. - Use qualitative data such as the opinions of teachers and parents. - Interview the clients receiving direct service. - Assess the project’s cost effectiveness. Evaluators Include a brief listing of all the key personnel involved in the evaluation and their responsibilities. Describe their qualifications, also. Resumes of all key personnel including independent evaluators are included as an appendix. |
| --- | --- |
| RED FLAG Your evaluation plan must establish a baseline. You can’t tell how far you’ve come unless you know where you’ve been. | Evaluation Questions A good evaluation starts with a good question. There are two types of evaluation questions- “outcome questions” and “process questions.” Every plan should contain both. Outcome questions are concerned with goals, objectives, and milestones. Essentially, is the project doing what it was designed to do? Examples of outcome questions include: - Have the goals, objectives, and milestones been met? - Were they met on time? - How many clients were served? - Did the project produce any unexpected benefits? Process questions are concerned with the strategies, activities, and management of the project. They look at the mechanics of the project. Examples of process questions include: - Is the project cost effective? - Are the strategies, activities, technologies, teaching techniques, or software appropriate for the target audience? - How do clients feel about the project? - What factors are keeping the outcomes from being met? Data Collection To conduct a proper evaluation, data must be collected. This requires time, expertise, and access. Therefore, the evaluation plan should describe: - What data is be collected? - How the data is to be collected? - Who will collect the data? - When the data is to be collected? Proper data collection methods: - Collect both quantitative and qualitative data. - Employ a variety of collection methods (e.g., surveys, analysis of student records, focus groups) - Use the sources described in goals, objectives, and milestones. - Collect all the data needed to answer the evaluation questions. - Employ many of the same methods used in the needs assessment. |
| RED FLAG Don’t just pledge that you’ll dedicate time money and resources to an evaluation, quantify it and make sure it is reflected in the budget. Reviewers check your budget for dedicated resources, be they in-kind or requested. | Data Analysis and Establishing a Baseline Progress can be measured only if it is compared with something else. Therefore, it is essential to establish a “baseline” of data. If an outcome is where you want to go with a project, a baseline is where you start. The data revealed in a detailed needs assessment can serve as a baseline. Baselines may be established by: - Establishing a control group. - Pre-testing clients. - Analyzing student records prior to receiving services. - Reviewing records from similar students in the previous school year. Dissemination Plan Sharing evaluation results maximizes a project’s benefit. Even unsuccessful projects can teach valuable lessons. A sound dissemination plan will spread news about the project both during the project’s implementation and after the final evaluation. Dissemination not only lets other people know how well the project performed, but builds support for the project, as well. Before a dissemination plan can be devised, stakeholders must be identified. They may be reached through websites, TV, newspapers, radio, newsletters, presentations at conventions, reports to various groups or agencies, public meetings, and phone calls. Resources Evaluation and dissemination take time and money. A strong plan will discuss the resources dedicated to it. Expenses associated with an evaluation and dissemination plan might be: - Contracts for independent evaluators (amounts differ, but $3,000 to $10,000 is typical). - Substitutes if teachers are involved in focus groups or other evaluation activities. - Advertising expenses for TV, radio or newspaper. - Expenses associated with hosting a website. - Contracted services for website, newsletter, or flyer design. - Software for data analysis. - Temporary employee to enter the data. Evaluations take time, The evaluation plan should state how long it should take to accomplish the evaluation and demonstrate that enough person hours have been dedicated to completing it. |

| RED FLAG Everything said about a partner in the management plan should appear in the letter of commitment. Partnerships fall apart when partners fail to spell out, in detail, everyone’s roles and responsibilities. When partnerships fall apart, projects fall apart. | THE MANAGEMENT PLAN Many programs fail due to weak management. Some of the most common mistakes are: - Failure to start on time. - Failure to submit required reports. - Failure to regularly monitor performance of the project during implementation. - Failure to keep adequate documentation. - Failure to assure continuity and quality of the project in light of personnel turnover. - Failure to have an acceptable fiscal procedure in place. - Unauthorized budget deviations or account transfers. - Failure to form lasting partnerships in which all members recognize and fulfill their clearly- defined roles and responsibilities. - Failure to complete the project in a timely fashion. - A management plan describes, schedules, and assigns responsibilities for all the actions needed to carry out and support the implementation and evaluation plans. Relationships The management plan is based on the implementation and evaluation plans. Decisions about purchases, hiring, and curriculum development can be made only after these plans have been established. Buying computers makes sense only if you need them to employ a strategy or evaluate your success. Choosing a less effective strategy that uses computers because someone wants computers is backward engineering. Partners Partners are partners only if they contribute something to the project. While they may receive some compensation, organizations or companies that merely sell goods or services are vendors. The proposal should present a clear discussion of the project partners and include the following information: - Each partner’s respective role: why that partner is crucial to the project. - The specific contributions each partner will make in the forms of financial support, equipment, personnel, or other resources. The dollar amount of each contribution is reflected in the in-kind budget total. - What the partner hopes to gain through the partnership and participation in the project. - The partner’s expertise in dealing with the problem addressed in the needs assessment. |
| --- | --- |

| RED FLAG Make sure that there is a project director. Having one person in charge of all the little details makes for a smoother- running project. When there are too many people in charge, responsibilities get blurred and the project can lose direction. | The Steering Committee and Project Oversight Effective oversight is an important part of a well-run project. Every project should have a governing board known as a “steering committee,” which meets at least quarterly. Committee members should include representatives of all the major stakeholder groups. A stakeholder is anyone who has an interest in the project. Parents, teachers, and professionals are common stakeholder groups as are project partners, all of whom should have a representative who sits on the committee. A representative of the project’s clientele should be included on the committee, also. While the day-to-day decisions about the project should be left to the project director, the job of the steering committee is to make the major decisions. The committee should approve changes in policy, strategies, budget and outcomes. Mid-term and final evaluations should be submitted to and approved by the committee, as well. The committee may have other duties depending on the nature of the project. Staff List all of the key staff members involved with the project, their roles, responsibilities and qualifications. The minimum qualifications of perspective staff should be listed, as well. The amount of each staff member’s time dedicated to the project should be indicated; it should also be sufficient to properly manage the project. As a rule of thumb, project directors should dedicate at least 25%of their time to the project. |
| --- | --- |
| RED FLAG Detail is the key to successful management plans. If you have extra space in your proposal, you should add detail here. Short narratives and brief worksheets often mean hastily assembled projects. | Management Plan Worksheet Management actions are the tasks needed to implement and evaluate the project but do not provide direct service to clients. They are not the activities contained in the implementation plan. Examples of management actions include hiring staff, ordering supplies, installing computers, developing curricula, and conducting meetings. The management plan worksheet lists all the actions necessary to carry out the project. It provides dates and assigns responsibility for each management action. A well-considered management plan worksheet will: - Provide as much detail as can fit within the project narrative page limit. - Cover the entire grant period. - Include all major management actions. - Assign responsibility by job title (in case of personnel turnover). - Provide a range of dates for ongoing actions. Here’s an example of a management plan worksheet: |

| RED FLAG Don’t simply state that the project is part of an overall reform effort. State how. In addition, cite the specific goals, policies or efforts of that larger plan. Every statement of fact must be supported. | INTEGRATION WITH EDUCATION REFORM Projects are not run in a vacuum. They are often conducted in schools, and governed by local education agencies (LEAs). Successful projects must be aligned with the goals, efforts, and plans of these organizations. This section should present a discussion of how the project is part of a bigger picture. Some questions this section should answer are: - How does this project help meet the goals and objectives of the school improvement team plan? - How does this project fit into the local education agency’s master plan? - How does this project help meet MSDE educational standards (e.g., MSPAP, Core Learning Goals)? - How does this project help meet national education goals or fit into national initiatives (e.g., Goals 2000, Title I, etc.)? - Does this project coordinate efforts with any other projects currently underway? - Will resources be shared to increase efficiency and cost effectiveness? |
| --- | --- |

| RED FLAG Don’t count on more grants for future funds. Grants are generally meant as startup money. | FUTURE PLANS What happens to the project after the grant period? If it is worthwhile, the project should continue. Therefore, there needs to be a plan to maintain the project beyond the grant period. Partners Because a project depends on its partners, the partners should have a plan for their future relationship. Will the partnerships continue? If so, what new roles will each have? Beware of projects with partnership commitments that last only as long as the initial funding, especially if partners are receiving sizable compensation for their efforts. Make sure that any future plans for continued partnerships are stated in the letter of commitment. Plans for future funding Most projects will require financial resources to continue operating (e.g., wages, supplies, transportation). Although commitment should be made by the grantee to fund the financial obligations, LEAs may pledge only tentative support for future funding based on the project’s performance. A letter from a superintendent or other person of authority should be included to state the level of commitment to continuing the project beyond the funding period. This may appear in the appendix. There are other ways of insuring future funding. The project may begin charging for services, receive funding from an outside agency, or begin a campaign to raise funds from donations. Any plans to do these things should be detailed and should address any legal or ethical problems that may result. If a project cannot get sufficient financial commitments, plans for reducing project costs may be included. Plans might include switching to a volunteer workforce, reducing the number of clients, or eliminating the least cost-efficient services. Again, detailed plans should be provided. |
| --- | --- |

| Item Requested In-Kind Total SALARIES & WAGES Project Director (18 months @ $30,000/year) $22,500 $22,500 $45,000 Clerical Support (25% of time @ $20,000/Year for 18 months) $ 7,500 $ 7,500 TOTAL SALARIES & WAGES $22,500 $30,000 $52,500 CONTRACTED SERVICES Bus Transportation (2 buses X 4 trips X $200/bus/trip) $ 1,600 $ 1,600 TOTAL CONTRACTED SERVICES $ 1,600 $ 1,600 SUPPLIES & MATERIALS Notebooks for Professional Development Seminar (20X$10/ea) $ 200 $ 200 TOTAL SUPPLIES & MATERIALS $ 200 $ 200 TOTAL BUDGET $24,300 $30,000 $54,300 RED FLAG Does your budget contain money for a grant writer? This is not an allowable expense. Grant writers should be paid directly by your organization and not from grant awards. Only expenses incurred after the award has been made can be included in the budget. | BUDGET Both the project narrative and the budget describe the entire project. Needless to say, they should convey the same message. Everything mentioned in the project narrative must be reflected in the budget, and every budget line item must be stated or implied in the narrative. All expenses implied in the project narrative must be accounted for in the budget, either as requested funds or in-kind contributions. Budget Narrative The project’s budget narrative should cover every year of the project in detail. It should demonstrate that the budget is reasonable, cost-effective, and integrates other sources of funding. There should be no surprises in the budget. Reviewers will match the budget with the project narrative. All costs described in the project narrative must appear in the budget. The narrative justifies any line item expenses that are not obvious from the project narrative. Discuss how you estimated the cost of your line items, if it is not obvious. You should show why your budget is cost effective. Immediately following your justification, include a line item description using the format in the example. Group Line Items according to the following categories: Salaries & Wages, Contracted Services, Supplies & Materials, Other Charges, Equipment, and Transfers. Total each category. Each line must be detailed and specific. General expenses should be broken down into specific line items. For example, “meeting expenses” can be broken down into room rental, photocopying and refreshments. There is no page limit for the budget, so be as detailed as possible. Clearly show the requested funds and in-kind contributions for each line item. The budget narrative should follow the following four column format: Show how the expense was calculated for each line item. Reviewers will use this information to determine if your budget is reasonable and cost-effective. The chart on the preceding page is an example of a budget, which details the project’s expenses. Each expense is called a “line item,” and line items are grouped in categories called “objects.” There are six objects: - Salaries & Wages - Contracted Services - Supplies & Materials - Other Charges - Equipment - Transfers Each line item must contain the following information: - Description of the expense - Method of calculation - Amount requested - Amount contributed as in-kind - Total amount |
| --- | --- |

| RED FLAG Don’t “pad.” It’s sometimes hard to estimate the exact cost of certain items. So resist the temptation to put large sums next to line items like “supplies” or create unnecessary line items. This will raise suspicions for the reviewer. | Descriptions of line items must be concise and complete. Vague line items lack the detail reviewers need to understand what is being purchased. Expenditures may need to be broken down into multiple line items or described in greater detail. Here are some vague line items, followed by revisions: Vague Revised Supplies Supplies for professional development (notepads, overheads, etc.) Computer Lab 200 Mhz Computers Network Cards Laser Printers Cables Mileage Mileage for Project Director between schools Other examples of vague line items include contracted services, consulting, refreshments, transportation, and software. Each line item must show all the numbers used to calculate the number in the total column. Line items that are calculated using stipends or flat fees must be indicated as such. There should be no ambiguity as to how a number was derived. The in-kind column contains the contributions being made to the project. If the grant is a matching grant, the in-kind contributions must equal a percentage of the requested budget. Even if there is no required match, in-kind contributions should be indicated since it is important to demonstrate that the entire cost of the project is being covered. Percentages of an employee’s time are common in-kind contributions. Personnel listed in the in-kind column should be mentioned in the project narrative. The TOTAL column should indicate the entire expense of the project. |
| --- | --- |

| RED FLAG In-kind contributions of 1% to 10% of someone’s time are often meaningless as they most likely will not be regarded as a valid in-kind contribution. Listing a lot of highly paid people who donate very little time is not a good way of meeting matching grant requirements. | Here is a checklist of things reviewers will look at when examining your budget: - Budget follows the four-column format. - Total requested budget does not exceed the maximum award. - “Total amount requested” matches “amount requested” on cover sheet. - All columns add correctly. - Budget contains no vague line items. - All the line items are implied by the project narrative. - All expenses in the project narrative appear in the budget. - All items in the TOTAL column are derived from the calculations provided. - All costs are reasonable according to current market values. - All line items are justifiable and necessary. - There are no in-kind contributions for less than 10% of a person’s time. - Budget appears to be free from padding. - All expenses are incurred after the grant is awarded. - There are resources budgeted for evaluation and dissemination. - Budget summary sheet is included. Budget Summary Sheet The budget summary sheet is required of all MSDE grants and should follow the budget. There should be a copy of the Budget Summary Sheet inside the RFP. |
| --- | --- |

| RED FLAG Appendices must match the rest of the proposal. Reviewers will try to verify what you say about a partner or a staff member by looking in the résumés or letters of commitment. RED FLAG Don’t include thick appendices of irrelevant information. If it seems overwhelming, reviewers may not read it. All the essential information about your project should be in the project narrative and budget. | APPENDICES Appendices contain relevant information not required in the project narrative. The appendices may not be used to circumvent the page limit. Required appendices include the assurances, resumes of key personnel, and letters of commitment. Assurances The assurances page is a legal document regarding the duties of all grant recipients. It must be signed and dated by your superintendent or the head of your agency. Resumes Resumes of all key personnel must be included. Resumes should not extend beyond one page and should contain only qualifications directly related to the project. Letters of Commitment There should be a letter of commitment from each of the project partners and each school involved, signed by the principal and the entire SIT. All letters should be addressed to the lead organization, not to MSDE or any MSDE official. A good letter of commitment will: - Indicate that the partner knows and supports the goals and objectives of the project. - Describe the partner’s roles and responsibilities in the project. - Describe and quantify the partner’s contributions to the project. - Acknowledge all relevant information mentioned about the partner in the project narrative. - State what the partner hopes to gain through involvement in the project. - Other Appendices - All the critical information should be in the budget and project narrative. However, you may wish to include other information to flesh out their proposal. These can be helpful and might include: - Letters from users of the project’s services. - Examples of curricula or surveys. - Detailed data from a needs assessment. - Letters of support from elected officials, stakeholders, or nonprofit agencies. |
| --- | --- |

- Why All The Fuss?

When faced with the complex process of grant writing, the grant writer may question whether or not the money is worth the effort.   After all, why doesn’t MSDE just give you the money?  In a perfect world, it would be that easy. Many studies have shown and many project directors can testify that a good project starts with a good plan.  Grants management often requires Herculean efforts and the sharpest managerial skills.  As it has often been said, “The only thing worse than not getting the money is getting the money.”    A good plan now will save you time and agony later.  If you develop the grant correctly, anyone can pick up your proposal and know what needs to be done, when it needs to be done, and where it needs to be done.    If your plan is that good, you’re halfway there.

Good Luck!